## Cross-Browser Compatibility
| Project Name | saucedemo
| Module Name | Cross-Browser Compatibility
| Created By | Abu Talha
| Creation Date | 2024-01-07
Review By
Review Date
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Test Data | Post condition | Expected Result | Actual Result | Status | Executed by | Executed dates | Comment (if any Need)
TS_SD_001 | Cross-Browser Compatibility | TC01 | Verify Website on Google Chrome | 1. Open Google Chrome. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Google Chrome | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Google Chrome. | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_002 | Cross-Browser Compatibility | TC02 | Verify Website on Mozilla Firefox | 1. Open Mozilla Firefox. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out.1 | User has access to Mozila FIrefox | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Mozila Firefox | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_003 | Cross-Browser Compatibility | TC03 | Verify Website on Microsoft Edge | 1. Open Microsoft Edge. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Microsoft Edge. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Microsoft Edge. | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_004 | Cross-Browser Compatibility | TC04 | Verify Website on Safari | 1. Open Safari. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Safari | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Safari. | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_005 | Cross-Browser Compatibility | TC05 | Verify Website on Opera | 1. Open Opera 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Opera | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Opea | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_006 | Cross-Browser Compatibility | TC06 | Verify Website on Mobile Chrome | 1. Open Mobile Chrome. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Mobile Chrome. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Mobile Chrome. | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_007 | Cross-Browser Compatibility | TC07 | Verify Website on Mobile Safari | 1. Open Mobile Safari. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to Mobile Safari | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on Mobile Safari. | The website should function correctly without any display or functionality issues. |  | PASS | Abu Talha
TS_SD_008 | Cross-Browser Compatibility | TC08 | Verify Website on Different Resolutions | 1. Open a web browser. 2. Navigate to https://www.saucedemo.com/. 3. Change the screen resolution to multiple settings (e.g., 1024x768, 1280x1024, 1920x1080). 4. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to a device that can change screen resolutions. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | User has access to a device that can change screen resolutions. | The website should function correctly and be responsive across all tested resolutions. |  | PASS | Abu Talha
TS_SD_009 | Cross-Browser Compatibility | TC09 | Verify Website on Different Operating Systems | 1. Open a web browser on each operating system. 2. Navigate to https://www.saucedemo.com/. 3. Perform key actions such as login, add items to cart, proceed to checkout, and log out. | User has access to devices running different operating systems. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the website functions correctly on different operating systems (Windows, macOS, Linux). | The website should function correctly without any display or functionality issues on all tested operating systems. |  | PASS | Abu Talha

## Checkout_Process_Verification
| Project Name | saucedemo
| Module Name | Verify Checkout Process
| Created By | Abu Talha
| Creation Date | 6/27/2024
Review By
Review Date
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Test Data | Post condition | Expected Result | Actual Result | Status | Executed by | Executed dates | Comment (if any Need)
TS_SD_001 | Verify Checkout Process | TC01 | Proceed to Checkout with Items in Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Add items to the cart. 3. Click on the cart icon to view the cart. 4. Click on the "Checkout" button. | User is logged in and has items in the cart. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user can proceed to the checkout page with items in the cart. | he user should be navigated to the checkout page (https://www.saucedemo.com/checkout-step-one.html). |  | PASS | Abu Talha | 6/27/2024
TS_SD_002 | Verify Checkout Process | TC02 | Proceed to Checkout with Empty Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Ensure the cart is empty. 3. Click on the cart icon to view the cart. 4. Attempt to click on the "Checkout" button. | User is logged in and has an empty cart. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user cannot proceed to the checkout page if the cart is empty | The user should not be able to proceed to the checkout page, and an appropriate message should be displayed. |  | FAIL | Abu Talha | 6/27/2025
TS_SD_003 | Verify Checkout Process | TC03 | Verify Checkout Page Fields | 1. Proceed to the checkout page as described in TC01. 2. Check for the presence of "First Name," "Last Name," and "Postal Code" fields. | User is logged in and has items in the cart | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that all necessary fields are present on the checkout page. | All necessary fields should be present on the checkout page. |  | PASS | Abu Talha | 6/27/2026
TS_SD_004 | Verify Checkout Process | TC04 | Proceed to Next Step with Valid Information | 1. Enter valid information in the "First Name," "Last Name," and "Postal Code" fields. 2. Click on the "Continue" button. | user is logged in and on the checkout page with items in the cart. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user can proceed to the next step of the checkout process with valid information. | The user should be navigated to the next step of the checkout process. |  | PASS | Abu Talha | 6/27/2027
TS_SD_005 | Verify Checkout Process | TC05 | Proceed to Next Step with Invalid Information | 1. Enter invalid or incomplete information in the "First Name," "Last Name," and "Postal Code" fields. 2. Click on the "Continue" button. | User is logged in and on the checkout page with items in the cart. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user cannot proceed to the next step of the checkout process with invalid or incomplete information. | The user should not be able to proceed to the next step, and appropriate error messages should be displayed. |  | PASS | Abu Talha | 6/27/2028
TS_SD_006 | Verify Checkout Process | TC06 | Verify Order Summary | 1. Proceed to the final step of the checkout process. 2. Review the order summary details. | User is logged in and on the final step of the checkout process | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the order summary is correctly displayed on the order confirmation page. | The order summary should correctly display the items, quantities, prices, and total amount. |  | PASS | Abu Talha | 6/27/2029
TS_SD_007 | Verify Checkout Process | TC07 | Verify Order Confirmation Message | Click on the "Finish" button to place the order. | User is logged in and on the final step of the checkout process. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that an appropriate order confirmation message is displayed after placing the order. | An order confirmation message should be displayed, indicating that the order has been placed successfully. |  | PASS | Abu Talha | 6/27/2030
TS_SD_008 | Verify Checkout Process | TC08 | Verify Navigation to Order Confirmation Page | Click on the "Finish" button to place the order. | User is logged in and on the final step of the checkout process. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user is navigated to the order confirmation page after placing the order. | The user should be navigated to the order confirmation page. |  | PASS | Abu Talha | 6/27/2031
TS_SD_009 | Verify Checkout Process | TC09 | Verify Order Number Generation | Click on the "Finish" button to place the order. | User is logged in and on the final step of the checkout process. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that an order number is generated and displayed on the order confirmation page. | An order number should be generated and displayed on the order confirmation page. |  | PASS | Abu Talha | 6/27/2032
TS_SD_010 | Verify Checkout Process | TC10 | Verify Return to Home Page | Click on the "Back Home" button on the order confirmation page. | User is logged in and on the order confirmation page. | username: standard_user passwors: secret_sauce link: https://www.saucedemo.com/checkout-step-one.html | Verify that the user can return to the home page from the order confirmation page. | The user should be navigated back to the home page. |  | PASS | Abu Talha | 6/27/2033

## Shopping Cart Functionality
|  | Project Name | saucedemo
|  | Module Name | Shopping Cart Functionality
|  | Created By | Abu Talha
|  | Creation Date | 6/25/2024
Review By
Review Date
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Test Data | Post condition | Expected Result | Actual Result | Satus | Executed by | Executed dates | Comment (if any Need)
TS_SD_001 | Verify Shopping Cart Functionality | TC01 | Add Single Item to Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the "Add to cart" button for a specific product. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that a single item can be added to the cart. | The product should be added to the cart, and the cart icon should reflect the number of items |  | PASS | Abu Talha | 6/25/2024
TS_SD_002 | Verify Shopping Cart Functionality | TC02 | Add Multiple Items to Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the "Add to cart" button for a multiple product. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that multiple items can be added to the cart | All selected products should be added to the cart, and the cart icon should reflect the total number of items. |  | PASS | Abu Talha | 6/25/2025
TS_SD_003 | Verify Shopping Cart Functionality | TC03 | Add Same Item Multiple Times to Cart | 1.Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the "Add to cart" button for a specific product. 3. Click on the "Add to cart" button for the same product again. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that the same item cannot be added multiple times to the cart (since this is a common restriction in e-commerce sites). | The product should be added only once, and the cart icon should reflect the number of unique items |  | PASS | Abu Talha | 6/25/2026
TS_SD_004 | Verify Shopping Cart Functionality | TC04 | Verify Cart Badge Number | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the "Add to cart" button for several products. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that the cart badge number updates correctly when items are added. | The cart icon badge number should increase corresponding to the number of items added. |  | PASS | Abu Talha | 6/25/2027
TS_SD_005 | Verify Shopping Cart Functionality | TC05 | Add Item to Cart and Verify Cart Contents | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the "Add to cart" button for specific products. 3. Click on the cart icon to view the cart. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that the correct items are displayed in the cart after adding them. | The cart should display the correct items that were added. |  | PASS | Abu Talha | 6/25/2028
TS_SD_006 | Verify Shopping Cart Functionality | TC06 | Remove Single Item from Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the cart icon to view the cart. 3. Click on the "Remove" button for a specific product. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that a single item can be removed from the cart. | The product should be removed from the cart, and the cart icon should update accordingly. |  | PASS | Abu Talha | 6/25/2029
TS_SD_007 | Verify Shopping Cart Functionality | TC07 | Remove All Items from Cart | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the cart icon to view the cart. 3. Click on the "Remove" button for each product in the cart. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that all items can be removed from the cart. | All products should be removed from the cart, and the cart icon should reflect that the cart is empty. |  | PASS | Abu Talha | 6/25/2030
TS_SD_008 | Verify Shopping Cart Functionality | TC08 | Remove Item from Cart and Verify Cart Badge Number | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the cart icon to view the cart. 3. Click on the "Remove" button for a specific product. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that the cart badge number updates correctly when an item is removed. | The cart icon badge number should decrease corresponding to the number of items removed. |  | PASS | Abu Talha | 6/25/2031
TS_SD_009 | Verify Shopping Cart Functionality | TC09 | Remove Item from Cart on Product Page | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Add an item to the cart. 3. Click on the "Remove" button for the same product on the product page. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that an item can be removed directly from the product page after being added to the cart. | The product should be removed from the cart, and the cart icon should update accordingly. |  | PASS | Abu Talha | 6/25/2032
TS_SD_010 | Verify Shopping Cart Functionality | TC10 | Verify Cart is Empty Message | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on the cart icon to view the cart. | User is logged in and on the product page. | username: standard_user passwors: secret_sauce url: https://www.saucedemo.com/inventory.html. | Verify that an appropriate message is displayed when the cart is empty. | The cart page should display a message indicating that the cart is empty |  | FAIL | Abu Talha | 6/25/2033 | do not show any display message like that (cart is empty)

## Product Page Functionality -2
| Project Name | saucedemo
| Module Name | Product Page Functionality
| Created By | Abu Talha
| Creation Date | 6/23/2024
Review By
Review Date
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Test Data | Post condition | Expected Result | Actual Result | Satus | Executed by | Executed dates | Comment (if any Need)
TS_SD_001 | Product Page Functionality | TC01 | Sort Products by Name (A to Z) | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Select "Name (A to Z)" from the sort dropdown menu. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | The product list should remain sorted alphabetically from A to Z until the sort option is changed or the page is reloaded. | Products should be displayed in alphabetical order from A to Z |  | PASS | Abu Talha | 6/23/2024
TS_SD_002 | Product Page Functionality | TC02 | Sort Products by Name (Z to A) | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Select "Name (Z to A)" from the sort dropdown menu. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | The product list should remain sorted alphabetically from Z to A until the sort option is changed or the page is reloaded. | Products should be displayed in alphabetical order from Z to A |  | PASS | Abu Talha | 6/23/2024
TS_SD_003 | Product Page Functionality | TC03 | Sort Products by Price (Low to High) | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Select "Price (low to high)" from the sort dropdown menu. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | The product list should remain sorted alphabetically from low to High until the sort option is changed or the page is reloaded. | Products should be displayed in alphabetical order from low to high |  | PASS | Abu Talha | 6/23/2024
TS_SD_004 | Product Page Functionality | TC04 | Sort Products by Price (High to Low) | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Select "Price (Hign to low)" from the sort dropdown menu. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | The product list should remain sorted alphabetically from hign to low until the sort option is changed or the page is reloaded. | Products should be displayed in alphabetical order from hign to low |  | PASS | Abu Talha | 6/23/2024
TS_SD_005 | Product Page Functionality | TC05 | Verify Product Name | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Check the name of a specific product. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | Product name is same expected name | The product name should match the expected name. |  | PASS | Abu Talha | 6/23/2024
TS_SD_006 | Product Page Functionality | TC06 | Verify Product Price | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Check the price of a specific product. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | Verify that the product price is correctly displayed on the product page | he product price should match the expected price. |  | PASS | Abu Talha | 6/23/2024
TS_SD_007 | Product Page Functionality | TC07 | Verify Product Description | 1. Description: Verify that the product description is correctly displayed on the product page. 2. Preconditions: User is logged in and on the product page. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | Verify that the product description is correctly displayed on the product page. | The product description should match the expected description. |  | PASS | Abu Talha | 6/23/2024
TS_SD_008 | Product Page Functionality | TC08 | Verify Product Image | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Check the image of a specific product. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | Verify that the product image is correctly displayed on the product page. | The product image should be clear and correctly correspond to the product |  | PASS | Abu Talha | 6/23/2024
TS_SD_009 | Product Page Functionality | TC09 | Verify Product Details Navigation | 1. Navigate to https://www.saucedemo.com/inventory.html. 2. Click on a specific product. | "Valid URL Test Data" | https://www.saucedemo.com/inventory.html. username: standard_user passwors: secret_sauce | Verify that clicking on a product navigates to the product details page. | The user should be redirected to the product details page with correct information. |  | PASS | Abu Talha | 6/23/2025

## Test Case of Login Page
| Project Name | saucedemo |  | Test Case
| Module Name | Login Page |  | Pass | 17
| Created By | Abu Talha |  | Fail | 1
| Creation Date | 6/13/2024 |  | Not Executed | 0
| Review By |  |  | Out of Scoop | 0
| Review Date |  |  | Total
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Test Data | Post condition | Expected Result | Actual Result | Satus | Executed by | Executed dates | Comment (if any Need)
TS_SD_001 | verify the login functionality of saucedemo | TC01 | Login with Valid Credentials. | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid username in the "Username" field. 3. Enter a valid password in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: standard_user passwors: secret_sauce | user should able see home page | Succesfull login |  | PASS | Abu Talha | 6/22/2024
TS_SD_002 | verify the login functionality of saucedemo | TC02 | Login with Invalid Credentials | 1. Navigate to https://www.saucedemo.com/. 2. Enter a invalid username in the "Username" field. 3. Enter a invalid password in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: xxxxxxxxxx passwors: yyyyyyyyyyy | user should able to see pop up message invalid login | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2025
TS_SD_003 | verify the login functionality of saucedemo | TC03 | Login with Invalid Password | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid username in the "Username" field. 3. Enter a invalid password in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: standard_user passwors: xxxxxxxxxxx | user should able to see pop up message invalid password | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2026
TS_SD_004 | verify the login functionality of saucedemo | TC04 | Login with Invalid Username | 1. Navigate to https://www.saucedemo.com/. 2. Enter a invalid username in the "Username" field. 3. Enter a valid password in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: XXXXXXXX passwors: secret_sauce | user should able to see pop up message invalid username | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2027
TS_SD_005 | verify the login functionality of saucedemo | TC05 | Login with Blank Username | 1. Navigate to https://www.saucedemo.com/. 2. Leave the "Username" field blank. 3. Enter a valid password in the "Password" field. 4. Click on the "Login" button. | Valid URL none | username: passwors: secret_sauce | Username is required | Epic sadface: Username is required |  | PASS | Abu Talha | 6/22/2028
TS_SD_006 | verify the login functionality of saucedemo | TC06 | Login with Blank Password | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid valid username in the username field. 3. Leave the "Password" field blank.. 4. Click on the "Login" button. | Valid URL none | username: standard_user passwors: | Password is required | Epic sadface:Password is required |  | PASS | Abu Talha | 6/22/2029
TS_SD_007 | verify the login functionality of saucedemo | TC07 | Login with Blank Username and Password | 1. Navigate to https://www.saucedemo.com/. 2. Leave the "Username" field blank. 3. Leave the "Password" field blank.. 4. Click on the "Login" button. | Valid URL Test Data | username: passwors: | Username is required | Username is required |  | PASS | Abu Talha | 6/22/2030
TS_SD_008 | verify the login functionality of saucedemo | TC08 | Verify Case Sensitivity of Username and Password | 1. Navigate to https://www.saucedemo.com/. 2. Enter the username with incorrect casing (e.g., "standard_user" instead of "Standard_Sser"). 3. Enter the password with incorrect casing. 4. Click on the "Login" button | Valid URL Test Data | username: Standard_User passwors: seCret_sAuce | Username and password do not match | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2031
TS_SD_009 | verify the login functionality of saucedemo | TC09 | Verify Login with Special Characters in Username | 1. Navigate to https://www.saucedemo.com/. 2. Enter a username with special characters (e.g., "user!@#"). 3. Enter a valid password in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: user!@# passwors: secret_sauce | Verify that the user cannot log in with a username containing special characters. | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2032
TS_SD_010 | verify the login functionality of saucedemo | TC10 | Login with SQL Injection | 1. Navigate to https://www.saucedemo.com/. 2. Enter a SQL injection string (e.g., "' OR '1'='1") in the "Username" field. 3. Enter a valid password or SQL injection string in the "Password" field. 4. Click on the "Login" button. | Valid URL Test Data | username: OR '1'='1" passwors: OR '1'='1" | Verify that the application is secure against SQL injection attacks during login. | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2033
TS_SD_011 | verify the login functionality of saucedemo | TC11 | Login with JavaScript Injection | 1. Navigate to https://www.saucedemo.com/. 2. Enter a JavaScript injection string (e.g., "<script>alert('test')</script>") in the "Username" field. 3. Enter a valid password. 4. Click on the "Login" button. | Valid URL Test Data | username: <script>alert('test')</script> passwors: secret_sauce | Verify that the application is secure against JavaScript injection attacks during login | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2034
TS_SD_012 | verify the login functionality of saucedemo | TC12 | Verify Account Lockout after Multiple Failed Attempts | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid username and an invalid password. 3. Click on the "Login" button. 4. Repeat steps 2 and 3 multiple times (5 times). | Valid URL Test Data | username: standard_user passwors: xxxxyyyyy | Verify that the user account gets locked after a certain number of failed login attempts. | Epic sadface: Username and password do not match any user in this service |  | FAIL | Abu Talha | 6/22/2035
TS_SD_013 | verify the login functionality of saucedemo | TC13 | Login with Leading and Trailing Spaces in Username | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid username with leading and trailing spaces (" standard_user "). 3. Enter a valid password. 4. Click on the "Login" button. | Valid URL Test Data | username: standard_user passwors: secret_sauce | Verify that the application trims leading and trailing spaces in the username field during login. | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2036
TS_SD_014 | verify the login functionality of saucedemo | TC14 | Login with Leading and Trailing Spaces in Password | 1. Navigate to https://www.saucedemo.com/. 2. Enter a valid username. 3. Enter a valid password with leading and trailing spaces ( " secret_sauce "). 4. Click on the "Login" button. | Valid URL Test Data | username:standard_user passwors: secret_sauce | Verify that the application trims leading and trailing spaces in the password field during login. | Epic sadface: Username and password do not match any user in this service |  | PASS | Abu Talha | 6/22/2037
TS_SD_015 | verify the login functionality of saucedemo | TC15 | Login with Browser Auto-fill | 1. Navigate to https://www.saucedemo.com/. 2. Use the browser's auto-fill feature to populate the "Username" and "Password" fields. 3. Click on the "Login" button. | Valid URL Browser has saved login credentials for the site | username:standard_user passwors:secret_sauce | user should able see home page | Succesfull login |  | PASS | Abu Talha | 6/22/2038
TS_SD_016 | verify the login functionality of saucedemo | TC16 | Verify Remember Me Functionality | 1. Navigate to https://www.saucedemo.com/. 2. Enter valid credentials in the "Username" and "Password" fields. 3. Check the "Remember Me" checkbox (if available). 4. Click on the "Login" button. 5. Log out and close the browser. 6. Reopen the browser and navigate to https://www.saucedemo.com/. | Valid URL Browser has saved login credentials for the site | username:standard_user passwors:secret_sauce | user should able see home page | Succesfull login |  | PASS | Abu Talha | 6/22/2039
TS_SD_017 | verify the login functionality of saucedemo | TC17 | Login with Different Locale Settings | 1. hange the browser's locale setting to a different language ( French, Spanish). 2. Navigate to https://www.saucedemo.com/. 3. Enter valid credentials in the "Username" and "Password" fields. 4. Click on the "Login" button. | none | username:standard_user passwors:secret_sauce | Verify that the login functionality works correctly with different browser locale settings. | Succesfull login |  | PASS | Abu Talha | 6/22/2040
TS_SD_018 | verify the login functionality of saucedemo | TC18 | Verify Error Message for Disabled User | 1. Navigate to https://www.saucedemo.com/. 2. Enter the username of the disabled account in the "Username" field. 3. Enter the corresponding password in the "Password" field. 4. Click on the "Login" button. | There exists a user account that has been disabled | username:standard_user passwors:secret_sauce | Verify that an appropriate error message is displayed when a disabled user attempts to log in. | Invalid Login |  | PASS | Abu Talha | 6/22/2041

## Test Scenario
| Test Scenario | Created By: Abu Talha
SL no. | Test Scenario ID | Test Scenario Description
1 | TS_saucedemo_001 | Verify the login Functionalality of https://www.saucedemo.com/
2 | TS_saucedemo_002 | Product Page Functionality sc-1: Product Sorting sc-2 : Product Details Verification
3 | TS_saucedemo_003 | Shopping Cart Functionality: sc-1: Adding Items to Cart sc-2: Removing Items from Cart
4 | TS_saucedemo_004 | Checkout Process: sc-1: Proceed to Checkout sc-2: Order Confirmation
5 | TS_saucedemo_005 | Cross-Browser Compatibility: sc-1: Browser Compatibility
6 | TS_saucedemo_006 | Mobile Responsiveness: sc-1: Mobile Device Testing
7 | TS_saucedemo_007 | Search Functionality: sc-1: Search Product
8 | TS_saucedemo_008 | Account Management: sc-1: Update Account Information
9 | TS_saucedemo_009 | Logout Functionality
10 | TS_saucedemo_010 | Error Handling and Edge Cases: sc-1: Invalid URL Access sc-2: Session Timeout Handling
11 | TS_saucedemo_011 | Accessibility and Usability: sc-1: Accessibility Compliance
12 | TS_saucedemo_012 | Performance Testing: sc-1: Load Testing
13 | TS_saucedemo_013 | Integration and Compatibility: sc-1: Integration with Third-Party Services
14 | TS_saucedemo_014 | Security Testing: sc-1: SQL Injection Test
15 | TS_saucedemo_015 | Language and Currency Switching: sc-1: Language and Currency Switching